| Call to Action #57 We call upon federal, provincial, territorial, and municipal governments to provide education to public servants on the history of Aboriginal peoples, including the history and legacy of residential schools, the United Nations Declaration on the Rights of Indigenous Peoples, Treaties and Aboriginal rights, Indigenous law, and Aboriginal–Crown relations. This will require skills-based training in intercultural competency, conflict resolution, human rights, and anti-racism. |  |  |  |
| --- | --- | --- | --- |
| ACTION | COMPLETION | PROGRESS | LEAD |
| Treaty 3 Anniversary – October 3, 2023 – Guest Speaker (Sarah Mainville) | 2023 | Complete | Collaborate with High School |
| National Day for Truth and Reconciliation – September 30th, 2026 – Municipal Employees are provided a paid STAT holiday | Annual Event | Annual | Municipality of Red Lake |
| National Day for Truth and Reconciliation – September 30th, 2026 – Blanket Exercise | Annual Event | Annual | RLIFC |
| Shared History Education Materials – Prepared by RLIFC and are on display at the Heritage Centre | 2025 | Complete | Monique Tougas |
| Shared History Education Materials | Target completion date of June 1, 2027 | In Progress | Lead – Kaaren Dannenman Support From – Carolyn Spicer – Trevor Osmond |
| ‘Red Power Rising’ film presented the at Heritage Centre | March 6th & 7th 2026 | Complete – Film available for the public at the Heritage Centre | Heritage Centre & RLIFC |
| Welcome Sign at Airport |  | In Progress – Waiting for Funding and/or 2026 Budget | Not in the 2026 budget – seeking a funding opportunity for 2027 |
| Welcome Sign at Harry’s Corner | October 2025 | Complete | Brenda Ginac |
| Rest area and Wayfinding Signage/Billboard on Nungesser Road | Ongoing | Ongoing – Verbal update to be provided December 2025 | Michelle – The Municipality continues to work with MTO |
| Land Acknowledgement Statement Developed and Displayed - Read at every Committee of Council - Included on Municipal Website - Included on Municipality’s Facebook Page - Included in Newsletter - Display at Municipal Office, Airport, Arena & Red Lake Community Centre - Heritage Centre | 2024 | Complete | Brenda Ginac |
| Council Adopt Diversity, Equity, Inclusion - and - Anti-Racism Policy | 2026 2026 | In Progress Complete | HR and Clerks Department – working on a policy |
| Implementation of Diversity, Equity, Inclusion - and - Anti-Racism Policy | 2026 2026 | In Progress Complete | HR and Clerks Department – working on a policy |
| Design on Lions Club Annual Ornament – Truth & Reconciliation | Target Completion Date of 2027 | In Progress – Discussions with Lions Club early 2026 | Carolyn Spicer |
| Presentation by an Elder at Age-Friendly Meeting | 2026 | In Progress – Discussions and confirmation with Age-Friendly Coordinator | TBD |
| 100th Anniversary of Gold Rush – Shared History Education Events | July 2025 | Complete | Monique Tougas and Kaaren Dannenman |
| Berens River Bridge Project Road South Committee | Target Completion Date of 2028 | In Progress – Construction to commence spring of 2026 | Provincial Government / MTO |
| National Indigenous Peoples Day Events | Annual Event | Annual | Red Lake Indian Friendship Centre |
| The Truth in Truth & Reconciliation Board Game | Purchased 2024 | Complete – Board game is available for use | See Municipal staff for access to game |
| New Hope Annual Ice Road Challenge – Bike in support of Pikangikum’s Bike Program | Annual Event | Annual | Municipality Collaborate with OPP |
| Teepee / Wigwam at Tikinagan | Unknown | In Progress – Location and details under discussion | Mayor |
| Removal of “Celebration” from 100 Anniversary Messages | July 2025 | Complete | N/A |
| The Truth in Truth and Reconciliation Board Game – Available at 100 Anniversary Event | July 2025 | Complete | Staff & Kaaren Dannenman |
| Shared History in Teepee at 100 Anniversary Event | July 2025 | Complete | Kaaren Dannenman |
| Opening Ceremony for New Welcome Sign | November 2025 | Complete | Committee Members |

| Call to Action #23 We call upon all levels of government to: - Increase the number of Aboriginal professionals working in the health-care field; - Ensure the retention of Aboriginal health-care providers in Aboriginal communities; - Provide cultural competency training for all health-care professionals. |  |  |  |
| --- | --- | --- | --- |
| Action | Completion | Progress | Lead |
| Collaborate with NOSM and University |  | The municipality has no responsibility for health care matters. However, we will continue to advocate with local health care professionals and the Ministry of Health. | Mayor, Council and CAO |
| Consult Keewaytinook (KO) Northern Chiefs |  |  |  |
| Consult with Anishnawbe Mushkiki Community Health and Wellness Aboriginal Health Access Centre |  |  |  |
| Consult with Pikangikum Health Authority |  |  |  |
| Consult with Lac Seul First Nation |  |  |  |
| Consult with Wabauskang First Nation |  |  |  |
| Consult with Treaty 3 |  |  |  |
| Consult with Red Lake Indian Friendship Centre |  |  |  |

| Call to Action #82 We call upon provincial and territorial governments, in collaboration with Survivors and their organizations, and other parties to the Settlement Agreement, to commission and install a publicly accessible, highly visible, Residential Schools Monument in each capital city to honour Survivors and all the children who were lost to their families and communities. |  |  |  |
| --- | --- | --- | --- |
| Action | Completion | Progress | Lead |
| Norseman Park Upgrades – Including cultural components Phase 1 | 2024 | Complete | Municipal staff |
| Norseman Park Upgrades – Including cultural components Phase 2 | Subject to Grant Approval and Funding | In Progress – Included in Council’s 2026 Budget | Municipal Staff |
| Norseman Park Upgrades – Including cultural components Phase 3 | Subject to Budget Approval and Grant Funding | In Progress – Budget proposed for 2027 | Municipal Staff |
| Norseman Park Plaque – Describing the history of the Norseman Plane as it relates to residential schools | To Be Determined | In Progress – Upon Parks Completion |  |
| Government Docks Turnaround – Added cultural components |  | Complete | Municipality |
| Survivors’ Flag at Phillip Thomas Vinet Centennial Park | 2024 | Complete | Brenda |

| Call to Action #92 We call upon the corporate sector to adopt the United Nations Declaration on the Rights of Indigenous Peoples as a reconciliation framework and to apply its principles, norms, and standards to corporate policy and core operational activities involving Indigenous peoples and their lands and resources. This would include, but not be limited to, the following: - Commit to meaningful consultation, building respectful relationships, and obtaining the free, prior, and informed consent of Indigenous peoples before proceeding with economic development projects. |  |  |  |
| --- | --- | --- | --- |
| Action | Completion | Progress | Lead |
| Meetings with Neighbouring Indigenous Leaders – Including Pikangikum, Wabauskang, Lac Seul, KO, Grand Council Treaty 3, Treaty 5, Treaty 9 |  | In Progress Municipality continues to attempt to find meeting dates. These will be reported when confirmed. | Mayor and Senior Staff |
| Friendship Accords with Neighbouring First Nations |  | In Progress Review and Re-sign document after the 2026 elections and display at Municipal Office. | TBD |
| First Nations Representation on Chukuni Communities Development Corporation Board | November, 2025 | Complete | Janet |

| Call to Action #93 We call upon the federal government, in collaboration with the national Aboriginal organizations, to revise the information kit for newcomers to Canada and its citizenship test to reflect a more inclusive history of the diverse Aboriginal peoples of Canada, including information about Treaties and the history of residential schools. |  |  |  |
| --- | --- | --- | --- |
| Action | Completion | Progress | Lead |
| Shared History Document of Red Lake Area |  | In Progress – Draft to be prepared – Submit for review early 2026 | See call to Action #57 |